## Phase 1 - Inventory
Room | Category | Detail | Status | Question for Juan
Stairway | Lighting | Extra bulb at base of stairs; round light at top landing — covered by hallway/landing fixtures, no dedicated fixture | Keep
Stairway | Flooring | Carpet, beige | TBD | Being replaced along with the rest of the flooring, or kept?
Stairway | Hardware | Metal railing/handrail | Keep
Stairway | Other | Electric sockets at top of stairs | Keep
Hallway (2nd Floor) | Lighting | 2 round flush-mount ceiling lights, warm-toned, medium size | Keep
Hallway (2nd Floor) | Flooring | Wood-look | TBD
Hallway (2nd Floor) | Paint | Pastel light pink | TBD
Hallway (2nd Floor) | Other | 5-level built-in storage unit between the two bedrooms; square AC vent in ceiling | Keep
Bathroom (Upstairs) | Lighting | 1 wall sconce, bar-style, fabric/frosted shade, warm bulb, above sink | Keep
Bathroom (Upstairs) | Flooring | Tile | TBD
Bathroom (Upstairs) | Cabinets | Vanity cabinet under sink | TBD
Bathroom (Upstairs) | Faucet | 2-handle faucet | TBD
Bathroom (Upstairs) | Sink | 1, existing | TBD
Bathroom (Upstairs) | Paint | White (vanity wall); tile shower area (marble-look, accent band) | Keep
Bathroom (Upstairs) | Doors | Wood, white paint, lever-style, good condition | Keep
Bathroom (Upstairs) | Windows | Small vent/exhaust window, minimal trim | Keep
Bathroom (Upstairs) | Other | 2 mirrors present (3ft unattached + framed hanging); storage shelving left of entrance; toilet functional; single-handle showerhead | TBD | Which of the 2 mirrors stays? Also: permit says fixtures 'remain in same locations' — same fixtures kept or new fixtures in same spots?
Orange Room (Bedroom, Upstairs) | Lighting | None installed; fire alarm bell present; light switch by door | TBD
Orange Room (Bedroom, Upstairs) | Flooring | Wood-look | TBD
Orange Room (Bedroom, Upstairs) | Paint | Yellow-orange-beige tone | TBD
Orange Room (Bedroom, Upstairs) | Doors | Wood, white paint, carved detail, lever-style, good condition | Keep
Orange Room (Bedroom, Upstairs) | Windows | 1 square window, white trim, curtain rod hooks (no curtains) | TBD
Orange Room (Bedroom, Upstairs) | Other | 3 electric sockets; corkboard (likely removed) | Replace
Blue Room (Bedroom, Upstairs) | Lighting | Chandelier — ~3.5ft hanging shell-style, center of room, coastal theme | Replace | Keep or replace the shell chandelier?
Blue Room (Bedroom, Upstairs) | Flooring | Wood-look | TBD
Blue Room (Bedroom, Upstairs) | Cabinets | Hanging wall cabinet, glass front | TBD
Blue Room (Bedroom, Upstairs) | Paint | Very light blue, dark blue painted corner outline | TBD
Blue Room (Bedroom, Upstairs) | Doors | Wood, white paint, no carvings, lever-style, good condition | Keep
Blue Room (Bedroom, Upstairs) | Windows | 1 square window w/ blinds, white trim | TBD
Blue Room (Bedroom, Upstairs) | Other | 4 electric sockets; closet/storage compartment | Keep
Open Space (Downstairs Living Room) | Lighting | 4 fixtures: 2 chain-hung box/panel pendants; 1 lantern pendant near entry/pink wall (= the 'chandelier' from Juan's video); 1 globe pendant by stairs; 1 ceiling fan | Keep
Open Space (Downstairs Living Room) | Flooring | Tile, square, wood-look pattern | TBD
Open Space (Downstairs Living Room) | Paint | White, pastel pink accent wall | TBD
Open Space (Downstairs Living Room) | Doors | Main door (glass panel, gold knob, twist lock) + screen door (new brass deadbolt+knob); sliding glass door beside wood stove | Keep
Open Space (Downstairs Living Room) | Windows | 2 windows, white trim | TBD
Open Space (Downstairs Living Room) | Other | Wood stove/pot belly fireplace — officially scheduled for removal per permit, wall/siding patched after; baseboard mixed dark/white needs unifying; storage rooms under and left of stairs | Replace
Yellow Room (Downstairs) | Lighting | 1 flat circular ceiling light, flush-mount | Keep
Yellow Room (Downstairs) | Flooring | Wood-look | TBD
Yellow Room (Downstairs) | Paint | Wall color not confirmed (only ceiling damage/hole documented) | Flag | What's the actual wall paint color? Never explicitly confirmed.
Yellow Room (Downstairs) | Doors | Wood, white paint, round doorknob; connecting door to downstairs bathroom (regular knob, swinging) | Keep
Yellow Room (Downstairs) | Windows | 1 stained-glass window, wood-tone/gold trim | TBD | Keep or replace the stained-glass window?
Yellow Room (Downstairs) | Other | 4 sockets, 1 switch; curtain rod wider than the window | Keep
Bathroom (Downstairs) | Lighting | Classic 3-bulb 'Hollywood-style' fixture above sink/mirror | Replace
Bathroom (Downstairs) | Flooring | Tile | TBD
Bathroom (Downstairs) | Cabinets | Vanity cabinet under sink | TBD
Bathroom (Downstairs) | Faucet | Single-handle (up-down style) | TBD
Bathroom (Downstairs) | Sink | White, existing | TBD
Bathroom (Downstairs) | Paint | White | TBD
Bathroom (Downstairs) | Doors | Good condition | Keep
Bathroom (Downstairs) | Windows | Small vent window, minimal trim (same type as upstairs) | Keep
Bathroom (Downstairs) | Other | Bathtub behind glass sliding shower door, 3-handle faucet, heavy staining/mold buildup; 2 mirrors (1 + mirrored cabinet door); storage shelving left of entrance; connecting door to yellow room | Flag | Which mirror stays? Does the tub get cleaned, reglazed, or replaced given the staining?
Kitchen | Lighting | 12-pack recessed lights being added (Amazon); existing: 1 oval/sphere semi-flush (over sink), 1 flat circular (over white-cabinet side); no chandelier here | New
Kitchen | Flooring | Tile | TBD
Kitchen | Cabinets | Wood-tone run (12in, 15in x2, 24in corner, 24in, 30in, 36x36 Lazy Susan, 36in sink cabinet, 40in uppers) vs. different white-finish run opposite wall | TBD | Unify the two cabinet finishes, or leave two-tone?
Kitchen | Hardware | Being sourced from office stock | New
Kitchen | Countertops | Black laminate, chipped/worn front edge | Replace | Granite already acquired, in the office
Kitchen | Backsplash | White square tile, decent condition | TBD
Kitchen | Faucet | 2 separate existing faucets (center + pull-out sprayer) | TBD
Kitchen | Sink | Double-basin white, existing | TBD | Is the existing sink being replaced by the one sourced in the office, or kept?
Kitchen | Paint | Cream/yellow-white | TBD
Kitchen | Doors | Kitchen->garage door (wood, dirty, needs repaint); kitchen sliding glass door (vertical blinds); kitchen left-side wood+glass door (good) | Replace/Keep mix
Kitchen | Windows | 1 window, white trim | Keep
Kitchen | Appliances | Range hood, range, dishwasher, refrigerator (counter-depth, dims to Caesar) — all 4 replacing regardless of current condition. Tier: mid-to-upper, not bottom of the barrel, not Viking, not cheap | New
Garage | Lighting | 2 fixtures: 1 round, 1 linear/tube-style (~1 meter) | Keep
Garage | Flooring | Concrete, sealed/painted gray finish, stained/dirty in areas | TBD
Garage | Walls/Framing | Mixed — exposed studs w/ pink batt insulation (main bay/near garage door), white wall finish (near water heater) | TBD | Unify/finish out the framing, or leave as-is?
Garage | Storage | Built-in dark wood cabinet/hutch, 2 white cabinet units, 3 stored wood cabinet/box units | TBD
Garage | Doors | Garage door (exterior) needs replacement; kitchen->garage door wood, dirty, needs repaint | Replace | Is garage door replacement authorized under the permit ('repairing siding' only)?
Garage | Other | Water heater being repaired/re-strapped per permit; electrical panel/breaker box on stud wall near garage door (main panel repair item); wood blocking pieces on ceiling need removal for garage door clearance | Replace/Repair
Exterior | Signage | House numbers '1464' mounted near front entry | Keep
Exterior | Mailbox | None — mail slot built into door/wall instead | Keep
Exterior | Security | Small dome/bullet camera on exterior wall, 'Smile you're on camera' sign | TBD
Exterior | Lighting | 4 fixtures: black lantern (main entry/screen door); plain round light (back of wood-stove area); white coach lantern (kitchen slider); plain double-globe utility light (near gas/electric meter) | TBD
Exterior | Siding/Paint | Beige stucco — dry rot repair in scope; repainting exterior body IS in scope per permit wording ('paint interior and exterior') | Repaint
Exterior | Garage Door | Needs replacement | Flag | Confirm authorized beyond 'repairing siding,' or amend the permit
Exterior | Fence | Old wood, weathered | TBD | Outside strict permit scope (not siding) — confirm if authorized
Exterior | Patio | Brick pavers, existing, outside kitchen slider | Keep
Exterior | Windows | Front window glass being replaced per permit | Replace

## Phase 2 - Shopping Checklist
Room | Item | Needed? | Notes
Kitchen | Range hood | Yes | Mid-to-upper tier, not Viking, not cheap
Kitchen | Range/stove | Yes | Same tier as above
Kitchen | Dishwasher | Yes | Same tier as above
Kitchen | Refrigerator | Yes | Counter-depth — send dimensions to Caesar to verify fit
Kitchen | Cabinet hardware | Yes | Sourcing from office stock first
Kitchen | Sink | Maybe | Confirm if replacing existing or using office stock
Kitchen | Recessed lights | Yes | 12-pack, Amazon
Kitchen | Countertop (granite) | No | Already acquired, in the office
Bathroom (Upstairs) | Mirror | Maybe | Confirm which of the 2 stays first
Bathroom (Downstairs) | Tub reglaze/replace | Maybe | Pending Juan's decision on the mold staining
Bathroom (Downstairs) | Light fixture | Yes | Replacing the classic 3-bulb fixture
Blue Room | Chandelier | Maybe | Pending keep/replace decision
Yellow Room | Stained-glass window | Maybe | Pending keep/replace decision
Open Space | Paint (interior) | Yes | Full room, plus baseboard unification
Garage | Garage door | Yes | Precision quote on file — pending permit confirmation
Exterior | Exterior paint | Yes | In scope per permit wording
Whole House | Carpet | Yes | Empire Today quote on file, approved — schedule after paint

## Open Questions Summary
# | Question | Room | Status
1 | Bathroom fixtures (both) — same fixtures kept in place, or new fixtures in the same locations? | Both Bathrooms | Open
2 | Which mirror stays in each bathroom (2 present in each)? | Both Bathrooms | Open
3 | Downstairs tub — clean, reglaze, or replace given the mold staining? | Bathroom (Downstairs) | Open
4 | Kitchen sink — keep existing, or install the one sourced in the office? | Kitchen | Open
5 | Kitchen cabinets — unify the two finishes, or keep two-tone? | Kitchen | Open
6 | Blue room shell chandelier — keep or replace? | Blue Room | Open
7 | Yellow room stained-glass window — keep or replace? | Yellow Room | Open
8 | Yellow room's actual wall paint color — never confirmed. | Yellow Room | Open
9 | THE BIG ONE: garage door replacement, fence, landscaping, and pathway — confirm these are authorized beyond 'repairing siding,' or get the permit amended. | Garage / Exterior | Open

## Budget Tracker
Room | Item | Vendor | Price | Qty | Subtotal | Notes
Garage | Garage door replacement | Precision Garage Door | 2273.75 | 1
Whole House | Carpet installation | Empire Today (Ali) | 3275.03 | 1 |  | Approved by Juan; schedule after paint
Kitchen | Appliance package (hood/range/dishwasher/fridge) |  |  | 1 |  | Pricing pending — Phase 3 product research
Kitchen | Countertop (granite) |  | 0 | 1 |  | Already acquired, no additional cost expected
Exterior | Exterior paint |  |  | 1 |  | Pricing pending
Living Room/Ceiling | Joint compound, 18 lb Fast Set (Custom Building Products) | Building supply (San Rafael, CA) - HD card | 17.48 | 4 |  | Ceiling/drywall repair
Living Room/Ceiling | Vinyl drywall tape (Dryvit) | Building supply (San Rafael, CA) - HD card | 9.93 | 1
Living Room/Ceiling | FibaTape self-adhesive mesh drywall joint tape (Cofair ADFORS) | Building supply (San Rafael, CA) - HD card | 15.98 | 2
Living Room/Ceiling | Flexible paper corner tape, 100 ft (OX) | Building supply (San Rafael, CA) - HD card | 21.26 | 1
Living Room/Ceiling | Grout Boost compound (Custom Building Products) | Building supply (San Rafael, CA) - HD card | 15.11 | 15 |  | $2.32 discount applied on receipt
Grand Total