## PO Summary
52 Paramount Terrace: Final Material Purchase Summary
Tile, flooring and stone · 25% waste · recalculated from permit set A1-A7 (09/07/2026), bath plans, cabinet sheets and kitchen render · prepared 09/25/2026
Product | Recommended spec (CA contractor) | Where | Net SF (calc) | Waste | Order SF | Box / sheet coverage (SF) | Boxes to order | SF delivered | Status | Notes
Flooring | Rigid-core LVP (SPC), light natural oak look per render, ~9" x 60" plank, 20-mil wear layer, attached pad, waterproof | All rooms, 1F + 2F (not baths) | 1253.1549 | 25% | 1567 | 23 | 69 | 1587 | SCALED | Continuous with no transitions between rooms. Because every floor is new, the permit's 'match existing' note is met. Stairs are on Setting Materials. About 190 SF (halls, closets, stair landing) is scaled off the plan, so field verify.
Bath floor tile | 12" x 24" rectified porcelain, matte, DCOF >= 0.42 wet, warm light neutral | Baths 1, 2, 3 (outside shower) | 120.6897 | 25% | 151 | 15.5 | 10 | 155 | VERIFIED | One product and one dye lot for all 3 baths. Lay offset 1/3, not 1/2, to control lippage.
Shower wall tile | 12" x 24" porcelain, same series as the floor (or matching wall body), stacked or 1/3 offset | 3 showers, floor to ceiling | 250.0826 | 25% | 313 | 15.5 | 21 | 325.5 | VERIFIED | Includes window returns, niche returns and curb faces. Tile is inside the shower only.
Shower floor mosaic | 2" x 2" porcelain mosaic on 12" x 12" mesh, matte / slip-resistant, same color family | 3 shower pans | 37.671 | 25% | 48 | 10 | 5 | 50 | VERIFIED | Center drain with 1/4" per ft slope. Small tiles follow the 4-way slope.
Backsplash tile | 8" x 8" encaustic-look (cement pattern) porcelain per render | Kitchen, counter to uppers | 19.1389 | 25% | 24 | 10.76 | 3 | 32.28 | ASSUMPTION | Window sills are assumed 4" above the counter (render). If they're higher, re-run: the full band is 31.1 SF net / 39 SF order.
Quartz countertop | 3 cm quartz, white / soft-vein per render, eased edge, undermount sink | Kitchen + 3 curb caps + 3 niche sills | 33.181 | 25% | 42 | 55.125 | 1 | 55.125 | VERIFIED | 1 JUMBO slab (126" x 63"). Countertops fit either size, but only the jumbo leaves a 12" strip for the curb caps. See Countertop tab.
Unit for column H: boxes (tile/LVP), sheets-boxes (mosaic), slabs (quartz). Yellow cells = replace with the selected product's box coverage before release.
Breakdown by location (use for staging deliveries)
Location | Level | Floor tile net | Floor tile order | Wall tile net | Wall tile order | Mosaic net | Mosaic order | Total order SF
Bath 3 | 1F | 47.168 | 59 | 101.9266 | 128 | 17.3438 | 22 | 209
Bath 1 | 2F | 44.074 | 56 | 92.3418 | 116 | 11.7839 | 15 | 187
Bath 2 | 2F | 29.4477 | 37 | 55.8141 | 70 | 8.5434 | 11 | 118
Total |  | 120.6897 | 152 | 250.0826 | 314 | 37.671 | 48 | 514
Per-bath orders are rounded separately, so their sum can run 1-2 SF above the product total in the table above. Order to the product total.
Flooring by level
Level |  |  | Net SF |  | Order SF
1F |  |  | 461.2799 |  | 577
2F |  |  | 791.875 |  | 990
Total |  |  | 1253.1549 |  | 1567
Level totals are rounded per level, so they can run 1 SF above the flooring total.
Color key: Blue = input · Green = link to another tab · Black = formula · Yellow = replace with the selected product's data. Status: VERIFIED / SCALED / ASSUMPTION / RECOMMENDED / HOLD.
Note on G5: Placeholder box size. Replace with the selected product's actual box coverage.
Note on G6: Placeholder box size. Replace with the selected product's actual box coverage.
Note on G7: Placeholder box size. Replace with the selected product's actual box coverage.
Note on G8: Placeholder box size. Replace with the selected product's actual box coverage.
Note on G9: Placeholder box size. Replace with the selected product's actual box coverage.
Note on H10: Slab count comes from the layout check on the Countertop tab, not SF division.

## Assumptions
Assumptions & Inputs
Blue = input you can change. Every formula in the workbook reads from here. 52 Paramount Terrace, SF 94118 · Block/Lot 1166/043
Parameter | Value | Unit | Source / basis
Waste factor (all tile, flooring, stone) | 25% | % | User instruction: 25% on every line. Also covers pattern matching on the backsplash.
Bathroom wall / ceiling height | 101.125 | in | User-provided: 101 1/8". Shower tile runs floor to ceiling.
Countertop depth | 25.5 | in | 24" cabinet depth (2'-0" on the lower cabinet sheet) + 1.5" front overhang
Backsplash height (counter to underside of uppers) | 18 | in | Standard 36" counter to 54" upper bottom. The render shows tile running from counter to uppers.
Window sill height above countertop | 4 | in | From the render (short tile band under the sink window). FIELD VERIFY: sill heights for W3, W5 and W6 aren't on the plans.
Niche width (finished opening) | 12 | in | Recommended: 12" x 24" prefab waterproof niche, fits between 16" o.c. studs
Niche height (finished opening) | 24 | in | Recommended
Niche depth (tiled returns) | 3.5 | in | 2x4 stud cavity, less backer
Window return depth (W11 jambs/sill/head) | 5 | in | 2x4 wall + backer + tile. Field verify.
Curb face tile strip (outside 4.5" + inside 5") | 9.5 | in | Recommended 4.5" curb (CPC 408.5: 2"-9" above drain). The quartz cap covers the curb top.
Curb cap width (quartz) | 4.5 | in | Matches a 4 1/2" foam curb. At 4.5" two rows fit in the jumbo slab's 9.5" leftover strip (5" does not).
Bath 1 partition wall end (tiled) | 4.5 | in | Wall end exposed at the glass line
LFT mortar coverage (12x24, back-buttered) | 40 | SF/50 lb | Typical manufacturer range, 1/2" notch
Modified thinset coverage (mosaic, backsplash) | 80 | SF/50 lb | Typical, 1/4" square notch
Grout density (cementitious, sanded) | 0.058 | lb/in³ | ~100 lb/ft³
Waterproof foam backer board sheet | 32 | SF | 4'x8' sheet (Kerdi-Board / Wedi type)
Uncoupling / waterproof floor membrane roll | 54 | SF | Standard roll size (Ditra type)
Tile edge trim stick length | 98.5 | in | Standard 8'-2 1/2" profile. It's SHORTER than the 101 1/8" wall, so each edge needs 2 pieces or a 10' custom length.
Backer board / membrane overage | 15% | % | Cut waste on board

## Takeoff
Takeoff Detail: every line, every dimension
Dimensions in inches from the permit set, bath plans and cabinet sheets. Net SF = Length x Width x Count / 144, or the plan label SF x Count. Negative count = deduction.
ID | Product | Item | Location | Level | Length (in) | Width / Height (in) | Count (+/-) | Plan label SF | Net SF | Status | Source / notes
FLOORING: Rigid-core LVP, all rooms (bathrooms get tile)
F1 | Flooring | Bedroom 2 (room) | Bedroom 2 | 1F | 147.5 | 137.5 | 1 |  | 140.842 | VERIFIED | A2: 8'-8" + 3'-7 1/2" = 12'-3 1/2" wide x 11'-5 1/2"
F2 | Flooring | Bedroom 2 closet | Bedroom 2 | 1F | 103 | 24 | 1 |  | 17.1667 | SCALED | 2'-0" deep dimensioned, length scaled ~8'-7". Room + closet = 158 SF vs 156.9 SF label, which checks out.
F3 | Flooring | Bedroom 3 incl. closet | Bedroom 3 | 1F | 129 | 137.5 | 1 |  | 123.1771 | VERIFIED | A2: 10'-9" x 11'-5 1/2" = 123.2 SF (plan label 116 SF is low). Over new floor assembly on the garage slab, A7 detail 4.
F4 | Flooring | Laundry (W/D) | Laundry | 1F |  |  | 1 | 16.5 | 16.5 | VERIFIED | A2 plan label
F5 | Flooring | Linen | Linen | 1F |  |  | 1 | 11.8 | 11.8 | VERIFIED | A2 plan label
F6 | Flooring | Garage nook | Garage nook | 1F |  |  | 1 | 19.9 | 19.9 | VERIFIED | A2 plan label
F7 | Flooring | Hall | 1F Hall | 1F | 205 | 45 | 1 |  | 64.0625 | SCALED | Not dimensioned. Scaled ~17'-1" x 3'-9". Field measure.
F8 | Flooring | Entry / stair landing area | 1F Stairs | 1F | 151.5 | 81.5 | 1 |  | 85.7448 | SCALED | 12'-7 1/2" dimensioned, depth scaled ~6'-9"
F9 | Flooring | Less stair flight footprint | 1F Stairs | 1F | 77 | 33.5 | -1 |  | -17.9132 | SCALED | Stair treads are counted separately on Setting Materials
F10 | Flooring | Living room | Living room | 2F |  |  | 1 | 341 | 341 | VERIFIED | A3 plan label
F11 | Flooring | Kitchen & dining | Kitchen & dining | 2F |  |  | 1 | 252 | 252 | VERIFIED | A3 plan label
F12 | Flooring | Less base cabinets, window wall (excl. range) | Kitchen & dining | 2F | 133.875 | 24 | -1 |  | -22.3125 | VERIFIED | 34 1/4 + 34 1/8 + 19 1/2 + 46. Floating LVP installs AFTER the cabinets and doesn't go under them. It still runs under the range, fridge and DW.
F13 | Flooring | Less base cabinets, left wall (excl. DW and corner) | Kitchen & dining | 2F | 31.375 | 24 | -1 |  | -5.2292 | VERIFIED | 45 3/8 - 24 corner + 10 filler/cabinet
F14 | Flooring | Primary bedroom | Primary bedroom | 2F |  |  | 1 | 156 | 156 | VERIFIED | A3 plan label
F15 | Flooring | Pantry | Pantry | 2F |  |  | 1 | 20 | 20 | VERIFIED | A3 plan label
F16 | Flooring | Primary closet | Primary closet | 2F | 64 | 42 | 1 |  | 18.6667 | SCALED | 5'-4" dimensioned, depth scaled ~3'-6"
F17 | Flooring | Hall | 2F Hall | 2F | 38 | 90 | 1 |  | 23.75 | SCALED | Not dimensioned. Scaled ~3'-2" x 7'-6".
F18 | Flooring | Foyer | Foyer | 2F |  |  | 1 | 8 | 8 | VERIFIED | A3 existing-plan label (unchanged)
BATHROOM FLOOR TILE: outside the shower
BF1 | Bath floor tile | Room gross | Bath 3 | 1F | 67.5 | 137.625 | 1 |  | 64.5117 | VERIFIED | Bath plan 67 1/2" x 137 5/8" = 64.5 SF (matches label)
BF2 | Bath floor tile | Less shower pan | Bath 3 | 1F | 67.5 | 37 | -1 |  | -17.3438 | VERIFIED | Shower 67 1/2" x 37"
BF3 | Bath floor tile | Room gross | Bath 1 | 2F | 90.25 | 89.125 | 1 |  | 55.8579 | VERIFIED | Common bath 90 1/4" x 89 1/8" = 55.9 SF (label 60 SF is high)
BF4 | Bath floor tile | Less shower pan | Bath 1 | 2F | 37.5 | 45.25 | -1 |  | -11.7839 | VERIFIED | Shower 37 1/2" x 45 1/4"
BF5 | Bath floor tile | Room gross | Bath 2 | 2F | 70.25 | 77.875 | 1 |  | 37.9911 | VERIFIED | Primary bath 70 1/4" x 77 7/8" = 38.0 SF
BF6 | Bath floor tile | Less shower pan | Bath 2 | 2F | 32.375 | 38 | -1 |  | -8.5434 | VERIFIED | Shower 32 3/8" x 38"
SHOWER WALL TILE: inside the shower only, floor to ceiling
SW1 | Shower wall tile | Back wall (exterior, W11) | Bath 3 | 1F | 67.5 | 101.125 | 1 |  | 47.4023 | VERIFIED | Full room width
SW2 | Shower wall tile | Left side wall (valve wall) | Bath 3 | 1F | 37 | 101.125 | 1 |  | 25.9835 | VERIFIED
SW3 | Shower wall tile | Right side wall (niche wall) | Bath 3 | 1F | 37 | 101.125 | 1 |  | 25.9835 | VERIFIED | Interior wall shared with Bedroom 3
SW4 | Shower wall tile | Less window W11 | Bath 3 | 1F | 30 | 41.25 | -1 |  | -8.5938 | VERIFIED | W11 30" x 41 1/4" per A5 size (A5 mislabels its location)
SW5 | Shower wall tile | Add W11 returns (jambs, sill, head) | Bath 3 | 1F | 142.5 | 5 | 1 |  | 4.9479 | ASSUMPTION | Perimeter 2x30 + 2x41.25. Return depth per Assumptions.
SW6 | Shower wall tile | Niche returns (opening/back net zero) | Bath 3 | 1F | 72 | 3.5 | 1 |  | 1.75 | RECOMMENDED | Tiling the niche back replaces the wall tile cut out for the opening
SW7 | Shower wall tile | Curb faces | Bath 3 | 1F | 67.5 | 9.5 | 1 |  | 4.4531 | RECOMMENDED | Straight curb across the full width
SW8 | Shower wall tile | Back wall (exterior, valve wall) | Bath 1 | 2F | 37.5 | 101.125 | 1 |  | 26.3346 | VERIFIED
SW9 | Shower wall tile | Left side wall (niche wall) | Bath 1 | 2F | 45.25 | 101.125 | 1 |  | 31.7771 | VERIFIED | Interior wall
SW10 | Shower wall tile | Partition wall (door side) | Bath 1 | 2F | 37.5 | 101.125 | 1 |  | 26.3346 | VERIFIED | Full-height partition between the shower and the door
SW11 | Shower wall tile | Partition wall end at glass | Bath 1 | 2F | 4.5 | 101.125 | 1 |  | 3.1602 | ASSUMPTION | Exposed wall end
SW12 | Shower wall tile | Niche returns | Bath 1 | 2F | 72 | 3.5 | 1 |  | 1.75 | RECOMMENDED
SW13 | Shower wall tile | Curb faces | Bath 1 | 2F | 45.25 | 9.5 | 1 |  | 2.9852 | RECOMMENDED | Curb on the open (glass) side
SW14 | Shower wall tile | Back wall (exterior, valve wall) | Bath 2 | 2F | 32.375 | 101.125 | 1 |  | 22.7356 | VERIFIED
SW15 | Shower wall tile | Left wall (exterior, niche wall) | Bath 2 | 2F | 38 | 101.125 | 1 |  | 26.6858 | VERIFIED | W13 is outside the shower at 60" AFF, so there's no deduction
SW16 | Shower wall tile | Niche returns | Bath 2 | 2F | 72 | 3.5 | 1 |  | 1.75 | RECOMMENDED | Exterior wall: keep insulation behind the niche (see Showers tab)
SW17 | Shower wall tile | Curb faces (L-curb, 2 glass sides) | Bath 2 | 2F | 70.375 | 9.5 | 1 |  | 4.6428 | RECOMMENDED | 32 3/8" + 38"
SHOWER FLOOR MOSAIC
SM1 | Shower floor mosaic | Shower pan | Bath 3 | 1F | 67.5 | 37 | 1 |  | 17.3438 | VERIFIED
SM2 | Shower floor mosaic | Shower pan | Bath 1 | 2F | 37.5 | 45.25 | 1 |  | 11.7839 | VERIFIED
SM3 | Shower floor mosaic | Shower pan | Bath 2 | 2F | 32.375 | 38 | 1 |  | 8.5434 | VERIFIED
KITCHEN BACKSPLASH: patterned tile per render, counter to underside of uppers
BS1 | Backsplash tile | Left wall run (DW / corner) | Kitchen | 2F | 79 | 18 | 1 |  | 9.875 | VERIFIED | 115" wall run - 36" refrigerator
BS2 | Backsplash tile | Less W6 (corner window) in band | Kitchen | 2F | 12 | 14 | -1 |  | -1.1667 | ASSUMPTION | W6 12" wide. Tile below the sill only.
BS3 | Backsplash tile | Window wall run (sink / range / 46" base) | Kitchen | 2F | 169.875 | 18 | 1 |  | 21.2344 | VERIFIED | 34 1/4 + 34 1/8 + 19 1/2 + 36 + 46. Tile runs behind the range to the hood/upper.
BS4 | Backsplash tile | Less W5 (sink window) in band | Kitchen | 2F | 74.25 | 14 | -1 |  | -7.2188 | ASSUMPTION | W5 74 1/4". Render: no uppers over the window, tile below the sill only.
BS5 | Backsplash tile | Less W3 overlap with 46" counter | Kitchen | 2F | 36.875 | 14 | -1 |  | -3.5851 | ASSUMPTION | W3 starts ~133" from the corner; the counter ends at 169 7/8"
KITCHEN COUNTERTOP & STONE ACCESSORIES: 3 cm quartz, one jumbo slab (see Countertop tab)
CT1 | Quartz | Window wall, corner to range (sink) | Kitchen | 2F | 87.875 | 25.5 | 1 |  | 15.5612 | VERIFIED | 34 1/4 + 34 1/8 + 19 1/2, includes the corner square
CT2 | Quartz | Left wall leg to refrigerator | Kitchen | 2F | 53.5 | 25.5 | 1 |  | 9.474 | VERIFIED | 79" - 25 1/2" corner overlap
CT3 | Quartz | Right of range (46" base) | Kitchen | 2F | 46 | 25.5 | 1 |  | 8.1458 | VERIFIED | Shown in the render. Dashed on the cabinet sheet, so confirm it's in the cabinet order.
CT4 | Quartz | Shower curb caps (3) | Baths | 1F/2F | 183.125 | 4.5 | 1 |  | 5.7227 | RECOMMENDED | 67.5 + 45.25 + 70.375. Cut from the slab's 12" leftover strip.
CT5 | Quartz | Niche shelves / sills (3) | Baths | 1F/2F | 12 | 4 | 3 |  | 1 | RECOMMENDED | Pitched sill, slab remnant
Blue = typed dimension from drawings · Green = linked to Assumptions · Black bold = formula. Status: VERIFIED = dimensioned on drawings or plan label; SCALED = measured off the plan, so field verify; ASSUMPTION = inferred; RECOMMENDED = contractor recommendation.

## Countertop
Countertop & Slab Check
Quartz, 3 cm, eased edge (per render). The fabricator templates on site after the cabinets are set; nothing is cut off these drawings.
Input / check | Jumbo slab | Standard slab | Notes
Slab length (in) | 126 | 120 | Typical quartz sizes. Confirm with the supplier.
Slab width (in) | 63 | 55
Edge trim each side (in) | 1 | 1 | Factory edge removed
Saw kerf (in) | 0.25 | 0.25
Slab area (SF) | 55.125 | 45.8333
Countertop net SF (CT1-CT3) | 33.181 | 33.181
Countertop SF with waste | 41.4762 | 41.4762
Strip 1: CT1 length needed (in) | 87.875 | 87.875 | Sink piece
Strip 2: CT2 + CT3 + kerf (in) | 99.75 | 99.75
Usable length (in) | 124 | 118
Width left after two 25.5" strips (in) | 9.5 | 1.5 | Leftover strip for curb caps
Curb-cap rows that fit (at cap width + kerf) | 2 | 0
Curb caps total length needed (in) | 183.125 | 183.125 | 67.5 + 45.25 + 70.375
Countertops fit on one slab? | YES | YES
Curb caps also fit from the same slab? | YES | NO | The 3 niche sills (12"x4") come from the strip 1 remnant
Waste check: SF with waste <= slab SF? | YES | YES
RECOMMENDATION | ORDER 1 JUMBO |  | A jumbo 126"x63" slab covers all countertops, the 3 curb caps and the niche sills. A standard slab fits the countertops but not the caps.
Piece list (templated sizes will change slightly)
Piece | Length (in) | Depth (in) | Notes
CT1 Window wall, corner to range | 87.875 | 25.5 | sink cutout; undermount recommended
CT2 Left wall leg | 53.5 | 25.5 | seam at corner; not at the sink
CT3 Right of range | 46 | 25.5 | exposed end: finished/eased end
Curb cap Bath 3 | 67.5 | 4.5 | 4 1/2" wide, pitch 1/8" toward shower
Curb cap Bath 1 | 45.25 | 4.5 | 4 1/2" wide
Curb cap Bath 2 (L, 2 pcs) | 70.375 | 4.5 | 32 3/8" + 38", mitered corner
Niche sills x3 | 12 | 4 | 4" deep, pitched

## Showers
Shower Specifications (contractor recommendation)
Full glass enclosures, tile inside the shower only, floor to ceiling at 101 1/8". Based on the permit plans; field verify after framing.
Spec item | Bath 3 (1F) | Bath 1 (2F, common) | Bath 2 (2F, primary)
Shower size (in) | 67 1/2" x 37" | 37 1/2" x 45 1/4" | 32 3/8" x 38"
Pan area (SF) | 17.3438 | 11.7839 | 8.5434
Wall tile net SF | 101.9266 | 92.3418 | 55.8141
Tiled walls | 3: back (exterior, W11), left (valve), right | 3: back (exterior, valve), left, partition by door | 2: back (exterior, valve), left (exterior, W13 side)
Open side(s) / glass | Front (67 1/2") | Right side (45 1/4") | Front (32 3/8") + side (38"), 90° corner
Glass enclosure | Inline: fixed panel + 24" swing door | Inline: fixed panel + 24" swing door | Corner: door + fixed panel on the front, fixed return panel on the side
Glass spec | 3/8" tempered, 78" high, clear/low-iron, CRC R308.4.5 safety glazing | same | same
Door opening | Min. 22" clear (CPC 408.5). Swing out. | Min. 22" clear | Min. 22" clear. The 32 3/8" front leaves room for a ~24" door + ~8" panel.
Measure glass | After tile is complete | After tile is complete | After tile is complete
Niche | 1 @ 12" W x 24" H x 3 1/2" D, prefab waterproof | 1 @ 12" x 24" x 3 1/2" | 1 @ 12" x 24" x 3 1/2"
Niche location | Right wall (interior, shared with Bedroom 3), centered, bottom at ~42" AFF | Left wall (interior), centered, bottom at ~42" AFF | Left wall. It's an EXTERIOR wall, so keep insulation behind the niche (1" rigid foam + prefab niche) per Title 24, or confirm 2x6 framing.
Niche sill | Quartz remnant, pitched | Quartz remnant, pitched | Quartz remnant, pitched
Window in shower | W11 30" x 41 1/4": tempered glass, vinyl or fiberglass frame, sloped tiled sill, waterproofed returns | None | None (W13 is outside the shower)
Curb | 4 1/2" high foam curb, 67 1/2" long | 4 1/2" high, 45 1/4" long | 4 1/2" L-curb, 32 3/8" + 38"
Curbless? | Not recommended: needs framing recess | Not recommended: needs 2F joist recess, and the permit says no structural changes | Not recommended (same)
Curb cap | Quartz, 4 1/2" wide | Quartz, 4 1/2" wide | Quartz, 4 1/2" wide, mitered corner
Drain | 2" center drain with bonding flange, 4" square grate | 2" center drain, 4" square grate | 2" center drain, 4" square grate
Pan / waterproofing | Pre-sloped foam tray or mortar bed + bonded sheet membrane (CPC 408.7), flood test 24 hr before tile | same | same
Wall backer | 1/2" waterproof foam board, seams banded (A4: approved tile backer at wet areas) | same | same
Bath floor outside shower | Uncoupling membrane over subfloor, 12x24 porcelain | same (over 2F wood framing) | same
Edge trim | 2 vertical edges at the glass line, 101 1/8" each | 2 vertical edges | 2 vertical edges
Valve wall | Left side wall | Back wall | Back wall

## Setting Materials
Setting Materials & Accessories
Quantities come from the net SF on the Takeoff tab. Coverage rates are on the Assumptions tab. Confirm against the selected manufacturer's data sheets.
Item | Basis / formula | Qty (calc) | Order qty | Unit | Notes
LFT mortar, 50 lb (12x24 floor + walls + curbs) | (floor + wall tile net) x 1.10 / coverage | 10.1962 | 11 | bags | Large-and-heavy-tile mortar. Back-butter the 12x24s.
Modified thinset, 50 lb (mosaic + backsplash) | (mosaic + backsplash) x 1.10 / coverage | 0.78114 | 1 | bags | White thinset under light-colored tile
Grout: 12x24 porcelain (1/8" joint, 3/8" thick) | lb/SF = (L+W)/(LxW) x joint x depth x 144 x density | 20.8664 | 21 | lb | High-performance or urethane grout recommended in showers. Round to the manufacturer's pack.
Grout: 2x2 mosaic (1/8" joint, 1/4" thick) | same formula | 11.307 | 12 | lb | Epoxy grout recommended on shower floors
Grout: 8x8 backsplash (1/16" joint, 3/8" thick) | same formula | 1.0771 | 2 | lb | Unsanded
Waterproof foam backer board, 4'x8' | gross shower wall SF x (1+overage) / 32 | 9.2962 | 10 | sheets | Plus manufacturer seam band, corners, pipe seals and fasteners/washers
Pre-sloped shower tray or mortar bed kit | 1 per shower | 3 | 3 | each | Bath 3 tray must be trimmed to 67 1/2" x 37"
Bonding-flange shower drain, 2", 4" square grate | 1 per shower | 3 | 3 | each
Prefab foam shower curb | Bath 2 L-curb = 2 pcs | 4 | 4 | pcs | 4 1/2" high
Prefab waterproof niche, 12" x 24" | 1 per shower (user confirmed niches) | 3 | 3 | each | Bath 2 niche in exterior wall: add rigid foam behind
Uncoupling / waterproof floor membrane | bath floor net x (1+overage) / roll | 2.5702 | 3 | rolls | All 3 bath floors
Tile edge trim (vertical edges at glass) | 6 edges x 101 1/8"; stick 98.5" is too short, so 2 pcs per edge | 12 | 12 | sticks | Or order 3 m (118") custom lengths: 6 pcs
Tile edge trim, window W11 outside corners | 4 edges, 30" / 41 1/4" | 2 | 2 | sticks
100% silicone, color-matched | changes of plane, glass, curb, backsplash | 6 | 6 | tubes | Don't grout inside corners
Tile leveling clips + wedges | 12x24 tile count x 3 | 695.198 | 696 | clips | Order a 500- or 1,000-count kit
LVP stair treads + risers (1F to 2F) | Tread count not on plans; estimated | 14 | 14 | sets | HOLD: count the treads in the field. Stairs 'existing to remain' per A2.
LVP flush stair nose (top landing) | 1 at the 2F landing | 1 | 1 | pc
LVP reducer / transition to bath tile | 3 bath doorways | 3 | 3 | pcs | Match LVP to tile height. Check the tile + membrane build-up.
LVP end cap / threshold at exterior doors | 1F entry, 2F foyer to porch, hall to garage | 3 | 3 | pcs | Garage door is the rated self-closing door, so the threshold must not interfere with latching
Slab moisture test (Bedroom 3 and any 1F slab areas) | RH probe per ASTM F2170 | 1 | 1 | test | Required by most LVP warranties over concrete
Baseboard | All rooms get new flooring, so base comes off |  |  | LF | Field measure. Not part of this takeoff.

## Open Items & Risks
Open Items & Contractor Risks
Resolve the HOLD items before releasing the related PO line.
# | Item | Why it matters | Affects | Needed from | Priority
1 | Kitchen window sill heights (W3, W5, W6) | The backsplash is based on sills 4" above the counter (render). Each inch higher adds tile. Full band = 39 SF order vs 24 SF now. | Backsplash tile | Field measure | HOLD
2 | Cabinet sheet shows uppers in front of W5 and W3 | The render shows no uppers over the windows. The hanging cabinet sheet must be revised before the cabinet PO. | Cabinets, backsplash | Designer | HOLD
3 | Range hood not on the cabinet sheet | The render shows an insert hood in the uppers over the range. Confirm the hood model, CFM and duct route (A4 'RH'). | Cabinets, backsplash | Designer | HIGH
4 | 46" base right of the range | It's in the render but dashed on the cabinet sheet and missing from A3. It affects CT3 (8.1 SF) and 21 SF of backsplash. | Quartz, backsplash, cabinets | Owner / designer | HIGH
5 | Product box coverage | Summary column G has placeholder box sizes. Actual boxes change the SF delivered. | All tile, LVP | Supplier | HIGH
6 | Hall, closet and stair-landing areas are scaled | About 190 SF of flooring was scaled off the plan because it isn't dimensioned. The permit says 'do not scale drawings.' | Flooring | Field measure | MED
7 | Stair tread count | Not on the plans. Estimated at 14 treads. | Stair treads | Field count | MED
8 | Bath 2 niche in exterior wall | Insulation and Title 24 continuity behind the niche. Alternative: a corner shelf. | Niche, framing | Contractor / T24 | MED
9 | W11 inside the Bath 3 shower | Tempered glass is required. Waterproof the returns, slope the sill, use a vinyl or fiberglass frame. It's a leak and warranty risk. | Wall tile, window | Contractor | MED
10 | A5 window schedule locations mislabeled | W7 is labeled Bath 3 but is on 2F; W11 is labeled Primary Bedroom but is in the Bath 3 shower. Correct before permit issuance or inspection. | Windows | Designer | MED
11 | Plan area labels vs dimensions | Bath 1 label 60 SF vs 55.9 SF measured; Bedroom 3 label 116 SF vs 123.2 SF. This workbook uses dimensions. | Flooring, bath tile | Designer (FYI) | LOW
12 | Dye lot / lead time on patterned backsplash | Patterned tile is often special order. A short order later won't match. Order in one lot and keep 1 spare box. | Backsplash | Purchasing | MED
13 | Slab release | Reserve the slab by lot now. Fabricate only from the field template after cabinets are set. | Quartz | Fabricator | MED
14 | Uneven floors / slab | Leveling compound may be needed at Bedroom 3 (over garage slab) and at 2F. LVP needs 3/16" in 10' flatness. | Flooring | Contractor | LOW
15 | Bath 2 shower size | 32 3/8" framed-to-framed shrinks ~1" after board and tile. Verify it still meets the CPC 408.6 minimum (1,024 sq in, 30" circle). | Bath 2 shower | Contractor | LOW